## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Team
Project: Produktionssteuerungssystem
BBZW, Sursee
Team
Project start date: | 2025-01-27 | [10 empty] | Scrolling increment: | [5 empty] | 2
Milestone marker: | 1 | 1 |  |  | January | [6 empty] | February | [27 empty] | March
[5 empty] | 2025-01-29 | 2025-01-30 | 2025-01-31 | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-08 | 2025-02-09 | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25
Milestone description | Assigned to | Progress | Start | Days | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
Project development
Kick-Off & Setup |  | 25% | 2025-01-27 | 9
Projektplan & DB-Konzept |  |  | 2025-02-08 | 5
Create, Update, Funktionen & Programmablauf |  | 50% | 2025-01-31 | 15
Komplette DB-Anbindung |  |  | 2025-02-23 | 1 | bar: S
Lagerverwaltung & Reports |  | 10% | 2025-02-09 | 6
Design
Datenmodell & ER-Diagramm |  |  | 2025-02-18 | 4
SQL-Skripte |  |  | 2025-02-22 | 14
GUI Mockups & Validierungskonzept |  |  | 2025-03-10 | 6
OOP-Struktur & Vererbung |  |  | 2025-03-23 | 3
UI-Verfeinerung |  |  | 2025-02-03 | 120
Testing
GUI Tests |  |  | 2025-03-12 | 15
Unit-Tests & Fehlerbehandlung |  |  | 2025-03-04 | 5
Produktionsabläufe |  |  | 2025-04-24 | 5
Abschliessende Tests und Feinschlieff
Abgabe-Vorbereitung & Video
To add more data, Insert new rows ABOVE this one